## Sheet1
OrderNo | Color | FabricConstruction | UOM | FabricDetails | Width | GSM | RequiredQtyKgs | Buyer | BookingUnit | BookingReceiveDate | Unit | Final Confirmation | Buyer Team | 1st Shipment Date | Last Shipment Date | T&A Yarn date | T&A Knitting Start | T&A Knitting End | T&A Dyeing Start | T&A Dyeing End | T&A Deli. Start | T&A Deli. End | Fabric Notes | Event Day
270072 | College Green | 100% Cotton Single Jersey Peach Finish,Tumble Dry Combed US BCI | kgs | Body | 66 | 150 | 194 | Ralph Lauren | ESL | 2026-03-17 | ESL | No | Team Beta | 2026-04-05 | 2026-05-05 | 2026-03-07 | 2026-04-04 | 2026-04-17 | 2026-04-24 | 2026-05-08 | 2026-05-19 | 2026-05-22 | Needs approval | Day 5
270013 | Ash Heather | 100% Cotton Fleece Inside Brush,Peach Finish,Tumble Dry Combed BCI | kgs | Body | 70 | 430 | 5106 | Carhartt | ESL | 2026-03-04 | EKL | Yes | Team Alpha | 2026-04-06 | 2026-05-09 | 2026-03-17 | 2026-04-07 | 2026-04-17 | 2026-04-24 | 2026-05-10 | 2026-05-15 | 2026-05-25 | Check shrinkage | Day 2
270079 | Blue | 68% Tencel 27% Wool 5% Elastane 1X1 Rib Tumble Dry Combed BCI | kgs | Rib | 48 | 230 | 813 | M&S | ESL | 2026-03-20 | EFL | No | Team Delta | 2026-04-15 | 2026-05-21 | 2026-03-07 | 2026-04-01 | 2026-04-18 | 2026-04-22 | 2026-05-03 | 2026-05-16 | 2026-05-27 | No issues | Day 1
270052 | Blue Ice | 100% Organic Cotton 1X1 Rib Tumble Dry Combed Organic GOTS | kgs | Rib | 74 | 370 | 209 | Stanley Stella | DKL | 2026-03-16 | EFL | Pending | Team Alpha | 2026-04-23 | 2026-05-16 | 2026-03-09 | 2026-04-03 | 2026-04-19 | 2026-04-28 | 2026-05-05 | 2026-05-18 | 2026-05-25 | Needs approval | Day 5
270075 | Grey Marl | 100% Cotton Fleece Inside Brush,Tumble Dry Combed BCI | kgs | Body | 78 | 320 | 9045 | M&S | ESL | 2026-03-18 | EKL | Yes | Team Beta | 2026-04-26 | 2026-05-22 | 2026-03-08 | 2026-04-08 | 2026-04-15 | 2026-04-25 | 2026-05-06 | 2026-05-18 | 2026-05-27 | No issues | Day 2
270060 | French Navy | 85% Organic Cotton 15% Recycle Polyester Fleece Flat Dry,Inside Brush Combed Organic GOTS | kgs | Body | 68 | 280 | 1088 | Stanley Stella | DKL | 2026-03-17 | EFL | No | Team Delta | 2026-04-01 | 2026-05-07 | 2026-03-17 | 2026-04-06 | 2026-04-20 | 2026-04-24 | 2026-05-05 | 2026-05-15 | 2026-05-25 | Check shrinkage | Day 4
270040 | Crockery | 95% Cotton 5% Elastane 1X1 Rib Tumble Dry Combed BCI Traceable | kgs | Rib | 30 | 260 | 74 | C&A | EKWL | 2026-03-14 | EFL | Yes | Team Beta | 2026-04-21 | 2026-05-10 | 2026-03-10 | 2026-04-03 | 2026-04-13 | 2026-04-30 | 2026-05-02 | 2026-05-15 | 2026-05-25 | Needs approval | Day 4
270013 | Semi Bleach (Cypress / WIP H Brown Pigment Garment Dyed) | 100% Cotton Fleece Inside Brush,Peach Finish,Tumble Dry Combed BCI | kgs | Body | 70 | 430 | 5018 | Carhartt | ESL | 2026-03-04 | EKL | Yes | Team Beta | 2026-04-27 | 2026-05-06 | 2026-03-28 | 2026-04-04 | 2026-04-20 | 2026-04-25 | 2026-05-09 | 2026-05-15 | 2026-05-23 | Standard wash | Day 3
270092 | Brown Mix | 100% Cotton Single Jersey Tumble Dry Combed BCI | kgs | Body | 60 | 300 | 4411 | M&S | ESL | 2026-03-31 | EFL | No | Team Alpha | 2026-04-23 | 2026-05-13 | 2026-03-03 | 2026-04-07 | 2026-04-17 | 2026-04-24 | 2026-05-04 | 2026-05-12 | 2026-05-26 | No issues | Day 1
270089 | Aviator Navy | 100% Cotton Single Jersey Tumble Dry Combed US BCI | kgs | Body | 66 | 160 | 101 | Ralph Lauren | EKWL | 2026-03-28 | ESL | No | Team Beta | 2026-04-18 | 2026-05-19 | 2026-03-09 | 2026-04-01 | 2026-04-17 | 2026-04-25 | 2026-05-02 | 2026-05-18 | 2026-05-25 | No issues | Day 3
270064 | Rosewood | 100% Cotton Single Jersey Tumble Dry Combed BCI | kgs | Body | 64 | 150 | 86 | M&S | EKWL | 2026-03-15 | EFL | Yes | Team Alpha | 2026-04-15 | 2026-05-02 | 2026-03-03 | 2026-04-02 | 2026-04-20 | 2026-04-24 | 2026-05-06 | 2026-05-16 | 2026-05-27 | Check shrinkage | Day 4
270012 | check | 100% Cotton 1X1 Rib Tumble Dry Open End BCI | kgs | Rib | 64 | 300 | 130 | Carhartt | ESL | 2026-03-04 | EKL | No | Team Alpha | 2026-04-20 | 2026-05-20 | 2026-03-11 | 2026-04-04 | 2026-04-15 | 2026-04-26 | 2026-05-08 | 2026-05-17 | 2026-05-25 | Check shrinkage | Day 2
270068 | check | 100% Cotton Single Jersey Tumble Dry Combed BCI | kgs | Body | 64 | 150 | 66 | M&S | EKWL | 2026-03-15 | EFL | Yes | Team Gamma | 2026-04-22 | 2026-05-07 | 2026-03-31 | 2026-04-03 | 2026-04-15 | 2026-04-24 | 2026-05-06 | 2026-05-17 | 2026-05-24 | No issues | Day 3
270089 | Black | 98% Cotton 2% Elastane 1X1 Rib Tumble Dry Combed US BCI | kgs | Rib | 86 | 440 | 831 | Ralph Lauren | EKWL | 2026-03-28 | ESL | Yes | Team Beta | 2026-04-30 | 2026-05-07 | 2026-03-03 | 2026-04-03 | 2026-04-16 | 2026-04-27 | 2026-05-10 | 2026-05-17 | 2026-05-22 | Needs approval | Day 2
270074 | White | 95% Cotton 5% Elastane 1X1 Rib Tumble Dry Compact Regen-Agri | kgs | Rib | 64 | 400 | 165 | Tommy Hilfiger | EKWL | 2026-03-19 | EFL | Yes | Team Gamma | 2026-04-19 | 2026-05-16 | 2026-03-30 | 2026-04-07 | 2026-04-20 | 2026-04-30 | 2026-05-10 | 2026-05-15 | 2026-05-24 | Standard wash | Day 4
270012 | Semi Bleach (WIP H Brown Pigment Garment Dyed) | 100% Cotton Single Jersey Tumble Dry Open End BCI | kgs | Body | 56 | 220 | 1735 | Carhartt | ESL | 2026-03-04 | EKL | Pending | Team Alpha | 2026-04-09 | 2026-05-25 | 2026-03-14 | 2026-04-10 | 2026-04-16 | 2026-04-28 | 2026-05-04 | 2026-05-15 | 2026-05-23 | No issues | Day 5
270093 | Dark Indigo | 100% Cotton 1X1 Rib Tumble Dry Compact BCI | kgs | Rib | 64 | 280 | 110 | Tommy Hilfiger | ESL | 2026-03-30 | EFL | Yes | Team Beta | 2026-04-05 | 2026-05-11 | 2026-03-13 | 2026-04-02 | 2026-04-17 | 2026-04-28 | 2026-05-08 | 2026-05-18 | 2026-05-25 | Urgent priority | Day 1
270040 | Delicioso | 95% Cotton 5% Elastane 1X1 Rib Tumble Dry Combed BCI Traceable | kgs | Rib | 30 | 260 | 44 | C&A | EKWL | 2026-03-14 | EFL | Yes | Team Alpha | 2026-04-10 | 2026-05-22 | 2026-03-04 | 2026-04-05 | 2026-04-16 | 2026-04-28 | 2026-05-03 | 2026-05-14 | 2026-05-25 | Check shrinkage | Day 2
270012 | Semi Bleach (Cypress Pigment Garment Dyed) | 100% Cotton 1X1 Rib Tumble Dry Open End BCI | kgs | Rib | 64 | 300 | 108 | Carhartt | ESL | 2026-03-04 | EKL | Yes | Team Gamma | 2026-04-20 | 2026-05-12 | 2026-03-20 | 2026-04-01 | 2026-04-15 | 2026-04-25 | 2026-05-08 | 2026-05-16 | 2026-05-25 | Urgent priority | Day 4
270025 | Black | 100% Cotton Double Jersey Jacquard Peach Finish,Tumble Dry Combed US BCI | kgs | Body | 64 | 405 | 12111 | Ralph Lauren | ESL | 2026-03-11 | EFL | No | Team Delta | 2026-04-18 | 2026-05-27 | 2026-03-05 | 2026-04-04 | 2026-04-14 | 2026-04-22 | 2026-05-08 | 2026-05-15 | 2026-05-22 | Check shrinkage | Day 1